## Risk Assessment
SUPPLY CHAIN RISK ASSESSMENT
TOTAL RISK |  | HIGH IMPACT RISK
4 |  | 2
MEDIUM IMPACT RISK |  | LOW IMPACT RISK
2 |  | 1
NO. | HAZARD ( SUPPLY CHAIN ) |  | ROLE/PROCESS | SEVERITY | RISK LIKELIHOOD | IMPACT LEVEL | ASSIGNED TO | NECESSARY ACTION | STATUS
1 | Single-source critical supplier failure |  | Procurement, Production | Major Injuries (Severe Business Impact) | Likely | High | Alice | Develop alternate suppliers & increase safety stock | Actioned
2 | International port congestion / customs delay |  | Logistics, Customers | Minor Injuries (Moderate Impact) | Highly Likely | High | Ben | Reroute shipments & notify customers | Not Actioned
3 | Quality defects from a supplier batch |  | Production, QA | Major Injuries (Severe Business Impact) | Unlikely | Medium | Chen | Tighten incoming inspection & hold payments until corrected | Hold
4 | IT / TMS outage (tracking system down) |  | Logistics, Planning | Negligible Injuries (Minor Impact) | Likely | Low | Devi | Implement fallback manual tracking SOP | WIP
5 | Fuel price spike impacting transport costs |  | Finance, Transport | Minor Injuries (Moderate Impact) | Likely | Medium | Elias | Hedge contracts & optimize routes | Actioned

## Raw Sheet (hidden)
Likelihood | Count | Severity | Count
Highly Likely | 1 | Fatality | 5
Likely | 3 | Major Injuries | 4
Unlikely | 1 | Minor Injuries | 2
Highly Unlikely | 0 | Negligible Injuries | 1