## SC Gantt Chart
Stage | Start Date | End Date | Duration | Status
Supplier Negotiation | 2025-09-01 | 2025-09-03 | 2 | Completed
Procurement | 2025-09-04 | 2025-09-08 | 4 | In Progress
Production | 2025-09-09 | 2025-09-15 | 6 | Not Started
Shipping | 2025-09-16 | 2025-09-20 | 4 | Not Started

## SC Tracker
Task | Owner | Deadline | Status | Priority | Notes
Get supplier quotes | Ravi | 2025-09-01 | Done | High | Received 3 quotes
Approve supplier | Manager | 2025-09-02 | Pending | High
Create PO | Accounts | 2025-09-03 | Pending | Medium
Track shipment | Logistics | 2025-09-18 | Not Started | Low

## SC Action Plan
Goal | Action Step | Responsible | Due Date | Done?
Secure Supplier | Evaluate quotes | Ravi | 2025-09-01 | Yes
Secure Supplier | Negotiate terms | Manager | 2025-09-02 | No
Fulfill Order | Issue PO | Accounts | 2025-09-03 | No

## SC Budget
Item | Estimated Cost | Actual Cost | Variance
Raw Materials | 15000 | 14500 | -500
Packaging | 3000 | 3200 | 200
Transport | 5000 | 4700 | -300

## SC Timeline
Milestone | Planned Date | Actual Date | Remarks
Quote Approval | 2025-09-02 |  | Pending approval
PO Issued | 2025-09-03 |  | To be completed
Goods Received | 2025-09-21 |  | Not yet shipped

## Credits
Templates customized for Supply Chain Project Management
Created by: Discover Talent by Dr. Vinod